## Overview
Intern Daily Task Plan
Range | 2026-07-21 through 2026-10-01 (53 weekdays)
Starting point | Complete beginner to programming
Arc | JS fundamentals -> React -> React Native/Expo -> TypeScript & testing -> independent practice app -> EliteMobile onboarding -> supervised real contributions
How to use this sheet | Update the Status column on the 'Daily Tasks' tab each day (Not Started / In Progress / Done / Blocked). Checkpoint rows (highlighted green) mark milestone reviews - don't move to the next week until a checkpoint is genuinely Done.
Weeks 1-2 | Programming fundamentals from zero (JS, Git)
Weeks 3-4 | React fundamentals, ending in a checkpoint quiz app
Weeks 5-6 | React Native + Expo, navigation, device APIs
Week 7 | TypeScript + testing fundamentals
Weeks 8-9 | Independent practice app, ending in a demo checkpoint
Week 10 | Onboarding into the real EliteMobile codebase
Week 11 | Two supervised real contributions + final wrap-up

## Daily Tasks
Date | Day | Week | Task | Details | Status | Notes
2026-07-21 | Tue | Week 1 (Jul 21-24): Programming Fundamentals I | Dev environment | Finish the Expo Setup Guide (Node, Git, VS Code, Expo Go). Confirm node -v, npm -v, git --version all work. Create a GitHub account. Write and run a plain .js file with `node file.js` to prove the toolchain works end to end. | Not Started
2026-07-22 | Wed | Week 1 (Jul 21-24): Programming Fundamentals I | JS basics I | Variables (let/const), data types, operators, template literals. Exercise: a tip calculator script that takes a bill amount and prints the tip and total. | Not Started
2026-07-23 | Thu | Week 1 (Jul 21-24): Programming Fundamentals I | JS basics II | Conditionals (if/else, switch), comparison/boolean logic. Exercise: FizzBuzz, plus a script that turns a numeric score into a letter grade. | Not Started
2026-07-24 | Fri | Week 1 (Jul 21-24): Programming Fundamentals I | JS basics III | Loops (for, while), arrays basics. Exercise: sum an array of numbers, find the max, reverse a string without using .reverse(). | Not Started
2026-07-27 | Mon | Week 2 (Jul 27-31): Programming Fundamentals II + Git | Functions | Declarations vs. arrow functions, parameters/return values, scope. Exercise: refactor Week 1's scripts into reusable, named functions. | Not Started
2026-07-28 | Tue | Week 2 (Jul 27-31): Programming Fundamentals II + Git | Arrays deep dive | map/filter/reduce/forEach and when to use each. Exercise: given an array of worker objects with name/hoursWorked, compute total hours, filter anyone over 8 hours, and map to just names. | Not Started
2026-07-29 | Wed | Week 2 (Jul 27-31): Programming Fundamentals II + Git | Objects & destructuring | Object literals, nested objects, destructuring, spread/rest syntax. Exercise: model a simple job-ticket object and write functions that read/update it immutably (spread, never mutate directly). | Not Started
2026-07-30 | Thu | Week 2 (Jul 27-31): Programming Fundamentals II + Git | Async basics | Callbacks, Promises, async/await, fetch. Exercise: fetch a list of fake users from a public test API (e.g. jsonplaceholder.typicode.com) and print their names. | Not Started
2026-07-31 | Fri | Week 2 (Jul 27-31): Programming Fundamentals II + Git | Git & GitHub | init/add/commit/push, branches, pull requests, .gitignore. Exercise: push all of Weeks 1-2's exercises to a personal GitHub repo with an honest commit history (not one giant commit). | Not Started
2026-08-03 | Mon | Week 3 (Aug 3-7): React Fundamentals I | What is React? | Components, JSX, why a UI library exists. Set up a web practice project (Vite + React is fine). Exercise: a static 'profile card' component with hardcoded text. | Not Started
2026-08-04 | Tue | Week 3 (Aug 3-7): React Fundamentals I | Props | Passing data into components, composing multiple components. Exercise: make the profile card reusable - render 3 different people via different props. | Not Started
2026-08-05 | Wed | Week 3 (Aug 3-7): React Fundamentals I | State (useState) | Click counters, toggles, controlled state. Exercise: a counter app (+/- buttons) and a show/hide toggle. | Not Started
2026-08-06 | Thu | Week 3 (Aug 3-7): React Fundamentals I | Lists & keys | Rendering arrays with .map(), why key matters. Exercise: a to-do list from a hardcoded array, each item with a working 'remove' button. | Not Started
2026-08-07 | Fri | Week 3 (Aug 3-7): React Fundamentals I | Forms | Controlled inputs, checkboxes, handling submit. Exercise: extend the to-do list with a text input + 'Add' button that appends to state. | Not Started
2026-08-10 | Mon | Week 4 (Aug 10-14): React Fundamentals II | useEffect | Side effects, dependency arrays, cleanup functions. Exercise: a stopwatch/timer using setInterval inside useEffect. | Not Started
2026-08-11 | Tue | Week 4 (Aug 10-14): React Fundamentals II | Conditional rendering | Ternaries, &&, early returns, loading/error/empty states. Exercise: fake a loading delay before showing the to-do list, plus an empty-state message. | Not Started
2026-08-12 | Wed | Week 4 (Aug 10-14): React Fundamentals II | Composition | Breaking components apart, children, lifting state up. Exercise: refactor the to-do app into TodoList/TodoItem/AddTodoForm with state lifted to a parent. | Not Started
2026-08-13 | Thu | Week 4 (Aug 10-14): React Fundamentals II | Custom hooks | Extracting reusable logic. Exercise: write a useCounter hook and use it in two different components. | Not Started
2026-08-14 | Fri | Week 4 (Aug 10-14): React Fundamentals II | Checkpoint project | Build a small quiz app (multiple-choice questions, score tracking, restart button) combining everything from Weeks 3-4. | Not Started
2026-08-17 | Mon | Week 5 (Aug 17-21): React Native + Expo Fundamentals | Web -> mobile | View/Text/Image/ScrollView replace div/span/img. Exercise: `npx create-expo-app practice-app`, run it in Expo Go, rebuild the profile card with RN components. | Not Started
2026-08-18 | Tue | Week 5 (Aug 17-21): React Native + Expo Fundamentals | StyleSheet & Flexbox | StyleSheet.create, flexDirection/justifyContent/alignItems. Exercise: a header/body/footer layout using only Flexbox. | Not Started
2026-08-19 | Wed | Week 5 (Aug 17-21): React Native + Expo Fundamentals | Touch & input | Pressable, TextInput, Alert. Exercise: port the counter and to-do list into React Native components. | Not Started
2026-08-20 | Thu | Week 5 (Aug 17-21): React Native + Expo Fundamentals | Lists on mobile | FlatList vs. .map(), keyExtractor/renderItem. Exercise: render 50+ fake items with FlatList instead of ScrollView+map. | Not Started
2026-08-21 | Fri | Week 5 (Aug 17-21): React Native + Expo Fundamentals | Images & safe areas | Image/expo-image, SafeAreaView/useSafeAreaInsets. Exercise: add a header + avatar image that correctly avoids the phone's notch/status bar. | Not Started
2026-08-24 | Mon | Week 6 (Aug 24-28): Navigation, Styling, Device APIs | Expo Router basics | File-based routing, app/index.tsx, Link/router.push. Exercise: add a second screen and navigate to it with a route param. | Not Started
2026-08-25 | Tue | Week 6 (Aug 24-28): Navigation, Styling, Device APIs | Tab & stack nav | The (tabs) folder convention, nested _layout.tsx. Exercise: turn the practice app into a 3-tab app (Home / List / Profile). | Not Started
2026-08-26 | Wed | Week 6 (Aug 24-28): Navigation, Styling, Device APIs | Theming & reusable UI | Colors/spacing constants, avoiding magic numbers, small reusable atoms. Exercise: extract a colors.ts and a shared Button component used across all 3 tabs. | Not Started
2026-08-27 | Thu | Week 6 (Aug 24-28): Navigation, Styling, Device APIs | Device APIs I | Permissions model, expo-image-picker (or expo-location). Exercise: add a 'pick a photo from your library' button to the Profile tab. | Not Started
2026-08-28 | Fri | Week 6 (Aug 24-28): Navigation, Styling, Device APIs | Device APIs II | Local persistence (AsyncStorage/MMKV). Exercise: make the to-do list survive closing and reopening the app. | Not Started
2026-08-31 | Mon | Week 7 (Aug 31-Sep 4): TypeScript + Testing Fundamentals | TypeScript I | Why types, primitives, typing function params/returns, interface vs type. Exercise: add TypeScript to the practice app; type the to-do item shape. | Not Started
2026-09-01 | Tue | Week 7 (Aug 31-Sep 4): TypeScript + Testing Fundamentals | TypeScript II | Typing component props, optional props, union types, typing useState. Exercise: add proper prop types everywhere; fix every red squiggly. | Not Started
2026-09-02 | Wed | Week 7 (Aug 31-Sep 4): TypeScript + Testing Fundamentals | Why we test | Jest basics, expect/toBe/toEqual. Exercise: write 3 tests for a plain helper function (e.g. calculateTotal), no UI involved. | Not Started
2026-09-03 | Thu | Week 7 (Aug 31-Sep 4): TypeScript + Testing Fundamentals | Testing components | React Testing Library: render, screen.getByText, simulating a tap. Exercise: test that the counter's count increases on tap. | Not Started
2026-09-04 | Fri | Week 7 (Aug 31-Sep 4): TypeScript + Testing Fundamentals | Testing hooks | renderHook, testing a custom hook in isolation. Exercise: write tests for the useCounter hook from Week 4. | Not Started
2026-09-07 | Mon | Week 8 (Sep 7-11): Practice App Build (Part 1) | Planning day | Pick a small app idea (Habit Tracker, Recipe Box, Workout Log, etc.), sketch 3 screens on paper, write a short plan (data model, screens, user actions). Present the plan before writing any code. | Not Started
2026-09-08 | Tue | Week 8 (Sep 7-11): Practice App Build (Part 1) | Scaffold | New Expo TypeScript project, Expo Router with the 3 planned screens as empty placeholders, a theming/colors file. Get navigation working end to end before any real content. | Not Started
2026-09-09 | Wed | Week 8 (Sep 7-11): Practice App Build (Part 1) | Main list screen | Data model, FlatList of items, an 'add new item' form flow. | Not Started
2026-09-10 | Thu | Week 8 (Sep 7-11): Practice App Build (Part 1) | Detail screen | Tapping an item navigates to a detail view; add an edit or delete action. | Not Started
2026-09-11 | Fri | Week 8 (Sep 7-11): Practice App Build (Part 1) | Persistence | Wire up AsyncStorage/MMKV so data survives an app restart; write at least one test for the core data logic. | Not Started
2026-09-14 | Mon | Week 9 (Sep 14-18): Practice App Build (Part 2) & Wrap-Up | UI polish | Consistent spacing/colors, loading/empty states, small feedback touches (haptics or simple transitions, optional). | Not Started
2026-09-15 | Tue | Week 9 (Sep 14-18): Practice App Build (Part 2) & Wrap-Up | Error handling | Empty input, very long text, zero-items states. Add form validation. | Not Started
2026-09-16 | Wed | Week 9 (Sep 14-18): Practice App Build (Part 2) & Wrap-Up | Testing pass | Write tests for the 2-3 most important pieces of real logic (not just rendering). | Not Started
2026-09-17 | Thu | Week 9 (Sep 14-18): Practice App Build (Part 2) & Wrap-Up | Code review day | Review the practice app's code together; apply feedback on naming, duplication, and structure. | Not Started
2026-09-18 | Fri | Week 9 (Sep 14-18): Practice App Build (Part 2) & Wrap-Up | Demo day | Intern presents the finished practice app. This is the readiness checkpoint before moving into EliteMobile. | Not Started
2026-09-21 | Mon | Week 10 (Sep 21-25): Onboarding into EliteMobile | Get it running | Clone/open EliteMobile, install dependencies, run it via Expo Go or a simulator/emulator, read any README/CLAUDE.md notes. Click through every screen as a user would - no code reading yet. | Not Started
2026-09-22 | Tue | Week 10 (Sep 21-25): Onboarding into EliteMobile | Read the architecture | Walk one full module end to end (e.g. roster): entity -> usecase -> adapter -> viewModel -> screen. Draw a hand diagram of how a tap flows to a screen update. | Not Started
2026-09-23 | Wed | Week 10 (Sep 21-25): Onboarding into EliteMobile | Read the tests | Open a few *.test.tsx files; understand what's verified and how test doubles/mocked dependencies are wired in. | Not Started
2026-09-24 | Thu | Week 10 (Sep 21-25): Onboarding into EliteMobile | Trace a past fix | Pick one already-fixed, documented bug in the project and understand why it needed fixing by reading the surrounding code, not just the diff. | Not Started
2026-09-25 | Fri | Week 10 (Sep 21-25): Onboarding into EliteMobile | Shadow task | Pick one small flagged cleanup item, write up a plan to fix it, and review the plan with a mentor before touching any code. | Not Started
2026-09-28 | Mon | Week 11 (Sep 28-Oct 1): Real Contributions + Wrap-Up | First real fix | Implement Friday's plan, run the existing tests, confirm nothing breaks, open a small diff/PR for review. | Not Started
2026-09-29 | Tue | Week 11 (Sep 28-Oct 1): Real Contributions + Wrap-Up | Review + second task | Address review feedback on the first fix; pick up one more small, well-scoped task with mentor guidance. | Not Started
2026-09-30 | Wed | Week 11 (Sep 28-Oct 1): Real Contributions + Wrap-Up | Finish second task | Implement, test, get it reviewed. Start drafting a short 'what I learned' writeup. | Not Started
2026-10-01 | Thu | Week 11 (Sep 28-Oct 1): Real Contributions + Wrap-Up | Wrap-up | Final review of both contributions; intern presents a recap of the practice app and the EliteMobile fixes; discuss next steps. | Not Started